# Tutorial

### Goals:

To provide students with experience with Personal Software Process (PSP) scheduling.

### Strategy:

Work through a scenario of PSP schedule planning, tracking and projecting.

### Preparation:

Review PSP lecture.

### Procedure:

For each scenario, use the supplied data to:

- Calculate the planned sections of the task and schedule planning templates.

- Fill in the actual portion of the task and schedule planning templates

- Estimate the week on which the project is likely to be completed.

### Scenario 1:

L.C. plans to commit 3.5 hours each week to her next programming assignment and has estimated the necessary tasks as follows:

| Task | Planned hours |
| --- | --- |
| Plan | 1.0 |
| Design | 4.5 |
| Code | 5.0 |
| Compile | 0.5 |
| Test | 1.5 |

On week 1, she completes the plan and records 2.1 hours of activity. On week 2, she is unable to work on the assignment. On week 3 she records 4.3 hours and completes the design.

### Scenario 2:

J.P has a contract to write a program for a local small business. He plans to allocate 5 hours every week to this job and estimates the time for each task as follows:

| Task | Planned hours |
| --- | --- |
| Plan | 1.6 |
| Design | 4.9 |
| Design Review | 2.4 |
| Code | 10.3 |
| Code Review | 4.5 |
| Compile | 1.2 |
| Test | 6.8 |
| Post-mortem | 1.2 |

On week 1, J.P. spends 3 hours planning but the planning is not completed. On week 2, he spends a further 3.9 hours and completes both the plan and the design. On week 3, he works for 3.7 hours and completes the design review and starts coding. He works for 4.1 hours on week 4 and 4.0 hours on week 5 coding. Finally on week 6 when J.P. works for 4.5 hours, the coding, the code review and compiling is finished and testing starts. On week 7 he spends 2.9 hours but the testing is not yet complete.

Table C48  Task Planning Template Instructions

| Purpose | • To estimate the development time for each project task • To compute the planned value for each project task • To estimate the planned completion date for each task • To provide a basis for tracking schedule progress even when the tasks are not completed in the planned order |
| --- | --- |
| General | • Expand this template or use multiple pages as needed. • Include every significant task. • Use task names and numbers that support the activity and are consistent with the project work breakdown structure. |
| Header | Enter the following: • Your name • Today’s date • The project number • The instructor’s name |
| Task | • Enter a task number and name. List the tasks in the order in which you expect to complete them. • Select tasks that have explicit completion criteria, for example, planning completed, program compiled and all defects corrected, testing completed and all defects corrected, and so on. |
| Plan ( Hours | Enter the planned hours for each task. |
| Plan ( Planned Value | • Total the planned hours for all the tasks. • For each task, calculate the percent its planned hours are of total hours. • Enter this percentage as the planned value for that task. • The total planned value should equal 100. |
| Plan ( Cumulative Hours | Enter the cumulative sum of the plan hours down through each task. |
| Plan ( Cumulative Value | • Sum the planned values down through each task. • Before proceeding, complete the Schedule Planning Template down through Plan(Cumulative Hours. • Then complete the Schedule Planning and Task Planning templates together. |
| Plan Date ( Monday | • For each cumulative hours entry, find the plan cumulative hours entry on the Schedule Planning Template that equals or just exceeds it. • Enter the date from that row (of the Schedule Planning Template) as the plan date on the Task Planning Template. • If several weeks on the Schedule Planning Template have the same cumulative value, enter the earliest date. • Unless you made daily plans, pick the plan date as the Monday of the week during which completion for that task is planned. |
| Actual Date | As each task is completed, enter the completion date. |
| Earned Value | For each completed task, enter the planned value. |
| Cumulative Earned Value | As each task is completed, total all the earned value entries and enter that total beside the latest task that was completed. |

Table C47 Task Planning Template

| Student |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Instructor |  |

| Task | Plan | Actual |
| --- | --- | --- |
| Number | Name | Hours | Planned Value | Cumulative Hours | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value |
| Totals |  |  |

Table C50  Schedule Planning Template Instructions

| Purpose | • To record the estimated and actual hours expended by calendar period • To relate the task planned value to the calendar schedule • To calculate adjusted planned and earned values when tasks change |
| --- | --- |
| General | • Expand this template or use multiple pages as needed. • Complete it in conjunction with the Task Planning Template. |
| Header | Enter the following: • Your name • Today’s date • The project number • The instructor’s name |
| Week Number | • From the project start, enter a week number, typically starting with 1. • For very small projects, it may be more convenient to use days instead of weeks. |
| Date (Monday) | • Enter the calendar date for each week. • Pick a standard day in the week, for example, Monday. |
| Plan(Direct Hours | • Enter the planned number of direct project hours you expect to spend each week. • Consider non-work time such as vacations, holidays, and so on. • Consider other committed activities such as classes, meetings, and other projects. |
| Plan( Cumulative Hours | Enter the cumulative planned hours through each week. |
| Plan( Cumulative Planned Value | For each week, do the following: • Take the plan cumulative hours from the Schedule Planning Template. • On the Task Planning Template, find the task with nearest equal or lower plan cumulative hours and note its plan cumulative value. • Enter this cumulative value in the Schedule Planning Template for that week. • If the cumulative value for the prior week still applies, enter it again. |
| Actual | • During development, enter the actual direct hours, cumulative hours, and cumulative earned value for each week. • Determine status against plan by comparing the cumulative planned value and the actual cumulative earned value. |
| Adjusted Earned Value | Proportionately adjust the earned value up or down as tasks are added or deleted. The adjusted earned value compensates for these changes without requiring a complete new plan. |

Table C49  Schedule Planning Template

| Student |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Instructor |  |

|  |  | Plan | Actual |
| --- | --- | --- | --- |
| Week | Date | Direct | Cumulative | Cumulative | Direct | Cumulative | Cumulative | Adjusted |
| Number | Monday | Hours | Hours | Planned Value | Hours | Hours | Earned Value | Earned Value |